Total: $42,478.80

Concrete Strategies THM4A Haskell ($12,003.03 + $14,000.00 FOR 4 RIGS DOWN)

26/0356

10148 Loop Rd. Haskell

28-24”-1064’

89-30”-3382’

Contract Price: $165,041.00

Price per hole: $1,410.61

Days on site: 9

Estimated days remaining: 2

4/20/2026

5-24”-176’ 4” with 150’ casing

CZM-R

Rental CZM 160

Billy

Trevor

Lithko THM4A Data Yard ($2,642.43)

26/1551

10148 Loop Rd. Haskell

122-24”-2440’

Price per hole: $660.61

Days on site: 3

Estimated days remaining: 8

4/20/2026

4-24”-62’ 3” dry SS

HPM 180

Rental CZM 125 (rig 8)

Cipriano

Jose G

BAR Lake Palestine LP1 Package 2 ($5,924.98)

26/0250

4362 CR 309. Frankston

40-30”-1570’

32-36”-1472’

100-30”-1000’ BOLLARDS

Contract price: $254,774.00 FULLY CASED TURNKEY

Price per hole: $1,481.24 INCLUDING BOLLARDS

Days on site: 9

Estimated days remaining: 31

4/20/2026

4-30”-148’ 4” with 100’ casing

Sany Mandarin

Neal

Juan V

Miguel A

Nilson

Carmelo

Gustavo

Josue

Tommy

Fort Worth Civil Mustang LPBs ($1,110.00 @ $185 per lpb)

24/901

NWC of N Central Blvd & E Ovilla St. Red Oak

4/20/2026

6 30” LPBs

Cap

Toni

Eduardo

SFC Graford Water Tank Piers ($5,618.33)

627 W Division Ave. Graford

12-18”-384’

3-24”-96’

Contracting Price: $9,350.00

Price per hole: $623.33

Days on site: 5

Estimated days remaining: 0

4/20/2026

3-18”-101’ 3” with 75’ casing

1-24”-36’ 2” with 25’ casing

Sany Ryu

Jonathan

Hector M

United Forming DBU Carter School of Business ($1,180.00)

26/2800

3000 Mountain Creek Pkwy. Dallas

53-24”-2080’

37-30”-1679’

37-36”-2062’

4-42”-264’

Contract price: $77,290.00

Price per hole: $590.00

Days on site: 15

Estimated days remaining: 25

4/20/2026

1-24”-32’ 6” dry SS

1-36”-50’ 8” dry SS

CZM-T

Jose

Alfonso
Jesus

R2 ESD DENTON STILL WAITING ON LOG SHEET