Total: $67,509.96

Orion Victoria Service Center ($12,022.60)

26/2000

1506 John Stockbauer Dr. Victoria

51-18”-1377’

126-24”-4622’

2-30”-74’

Price per hole: $317.51

Days on site: 17

Estimated days remaining: 6

4/23/2026

7-24”-276’ 5” with 280’ casing

Sany 4

Luis R

Jhon

Agustin

Miguel Araiza

Fort Worth Civil Mustang LPBs ($2,220.00 @ $185 per lpb)

24/901

NWC of N Central Blvd & E Ovilla St. Red Oak

4/23/2026

12-24” LPBs

LPBS were drilled, backfilled, then redrilled

Cap

Toni

Eduardo

Archer Western South Mesquite BP 12 SHORING HOLES ($2,400.00)

25/0158

32.70978 N, 96.54184 W. Mesquite

30-30”-30’ each

Contract/Change Order Price: $18,000.00

Price per hole: $600.00

Days on site: 2

Estimated days remaining: 3

4/23/2026

4-30”-123’ 8” Shoring holes

Beast

Jose A

Omar

Hector M

Emerson

United Forming DBU Carter School of Business ($5,310.00)

26/2800

3000 Mountain Creek Pkwy. Dallas

53-24”-2080’

37-30”-1679’

37-36”-2062’

4-42”-264’

Contract price: $77,290.00

Price per hole: $590.00

Days on site: 16

Estimated days remaining: 24

4/23/2026

9-24”-265’ 5” dry SS

Sany Pikachu

Bobby

Jose Z

Jose Inez

Linbeck CCMC West Tower Change Order 5 ($5,500.00)

25/1783

908 Southland Ave. Fort Worth

1-36” noise test hole/remob

Price per noise test hole/remob: $5,500.00

4/23/2026

1-24”-15’ sound

CZM-D

Neal

Andrew

R2 ESD Denton Change Order ($5,000.00)

11-18”-440’

Price per hole: $1,250.00

Days on site: 3

Estimated days remaining: 0

4/23/2026

4-18”-146’ 9” with 80’ casing

YJ

Cory

Jose Izquierdo

BAR Lake Palestine LP1 Package 2 ($1,481.24)

26/0250

4362 CR 309. Frankston

40-30”-1570’

32-36”-1472’

100-30”-1000’ BOLLARDS

Contract price: $254,774.00 FULLY CASED TURNKEY

Price per hole: $1,481.24 INCLUDING BOLLARDS

Days on site: 11

Estimated days remaining: 29

4/23/2026

1-36”-67’ 7” with 43’ casing

Sany Mandarin

Jonathan

Juan V

Miguel A

Alfonso

Ronnie

Josue

Griezman

Carmelo

Nilson

Manns Project Steel Dragon Interior ($1,542.78)

26/1603

15060 Blue Mound Rd. Fort Wort

20-30”-300’

8-36”-120’

8-42”-120’

Contract price: $27,770 Dry

Price per hole: $771.39

Days on site: 1

Estimated days remaining: 18

4/23/2026

2-36”-34’ 5” dry SS

DF1

Robert

Alex F

Lithko THM4A Data Yard ($14,533.34 + $17,500.00 FOR 5 RIGS DOWN)

26/1551

10148 Loop Rd. Haskell

122-24”-2440’

Price per hole: $660.61

Days on site: 6

Estimated days remaining: 5

4/23/2026

22-24”-323’ 9” dry SS

CZM-R

Rent CZM 125 (rig 5)

Rent CZM 125 (rig 8)

Billy

Cipriano

Jose G