Total: $41,463.34

Orion Victoria Service Center (NOTHING COMPLETED)

26/2000

1506 John Stockbauer Dr. Victoria

51-18”-1377’

126-24”-4622’

2-30”-74’

Price per hole: $317.51

Days on site: 16

Estimated days remaining: 7

4/21/2026

ALL HOLES BACKFILLED; NO CONCRETE

Sany 4

Luis R

Jhon

Agustin

Miguel Araiza

Lithko THM4A Data Yard ($9,248.49)

26/1551

10148 Loop Rd. Haskell

122-24”-2440’

Price per hole: $660.61

Days on site: 4

Estimated days remaining: 7

4/21/2026

14-24”-241’ 7” dry SS

Rental CZM 125 (rig 5)

Rental CZM 125 (rig 8)

Cipriano

Jose G

Concrete Strategies THM4A Haskell ($18,214.85 + $14,000.00 FOR 4 RIGS DOWN)

26/0356

10148 Loop Rd. Haskell

28-24”-1064’

89-30”-3382’

Contract Price: $165,041.00

Price per hole: $1,410.61

Days on site: 10

Estimated days remaining: 1

4/21/2026

7-24”-247’ 2” with 210’ casing

1-30”-36’ 8” dry SS

CZM-R

Rental CZM 160

Billy

Trevor

ALL ELSE NO GO FOR WEATHER