Total: $48,873.50

Lithko THM4A Data Yard ($6,606.07)

26/1551

10148 Loop Rd. Haskell

122-24”-2440’

Price per hole: $660.61

Days on site: 5

Estimated days remaining: 6

4/22/2026

10-24”-128’ 5” dry SS

Rent CZM 125 (rig 5)

Rent CZM 125 (rig 8)

Cipriano

Jose G

Concrete Strategies THM4A Haskell ($5,642.43 + $14,000.00 FOR 4 RIGS DOWN)

26/0356

10148 Loop Rd. Haskell

28-24”-1064’

89-30”-3382’

Contract Price: $165,041.00

Price per hole: $1,410.61

Days on site: 11

Estimated days remaining: 0

4/22/2026

4-30”-143’ 5” dry SS

CZM-R

Rental CZM 160

Billy D

Trevor

BAR Lake Palestine LP1 Package 2 ($5,924.98)

26/0250

4362 CR 309. Frankston

40-30”-1570’

32-36”-1472’

100-30”-1000’ BOLLARDS

Contract price: $254,774.00 FULLY CASED TURNKEY

Price per hole: $1,481.24 INCLUDING BOLLARDS

Days on site: 10

Estimated days remaining: 30

4/22/2026

4-30”-149’ 0” with 100’ casing

Sany Mandarin

Neal

Juan V

Miguel A

Nilson

Carmelo

Gustavo

Josue

Alfonso

Archer Western South Mesquite BP 12 SHORING HOLES ($4,200.00)

25/0158

32.70978 N, 96.54184 W. Mesquite

30-30”-30’ each

Contract/Change Order Price: $18,000.00

Price per hole: $600.00

Days on site: 1

Estimated days remaining: 4

4/22/2026

7-30”-218’ 4” SHORING HOLES

3 holes backfilled

Beast

Toni

Hector M

Emerson

Power Plumbing Rockwall ($7,500.00)

26/2052

201 W Washigton. Rockwall

2-90”-20’

JOB IS DONE IN TWO TRIPS

Contract price: $15,000.00 FOR BOTH TRIPS

Price per hole: $7,500.00

Days on site: 1

Estimated days remaining: 1

4/22/2026

1-90”-10’ 4” dry SS

EX-60

Jose A

Howard

Jose Inez

Brian B

R2 ESD Denton Change Order ($5,000.00)

11-18”-440’

Price per hole: $1,250.00

Days on site: 2

Estimated days remaining: 1

4/22/2026

4-18”-140’ 9” with 80’ casing

YJ

Cory

Alex F

ALL ELSE NO GO FOR WEATHER