Total: $58,483.10

Orion Victoria Service Center ($15,457.63)

26/2000

1506 John Stockbauer Dr. Victoria

51-18”-1377’

126-24”-4622’

2-30”-74’

Price per hole: $317.51

Days on site: 18

Estimated days remaining: 5

4/24/2026

9-24”-356’ 7” with 360’ casing

Sany 4

Luis R

Jhon

Agustin

Miguel Araiza

Potter West Worth Ballards

CAN’T FIND BID; DATA FROM CALENDAR

4/24/2026

34-18”-133’ 3” ballards

1-24”-11’ 0” ballard

YJ

Cory

Alex F

Lithko THM4A Data Yard ($3,963.64 + $21,000.00 FOR 6 RIGS DOWN)

26/1551

10148 Loop Rd. Haskell

122-24”-2440’

Price per hole: $660.61

Days on site: 7

Estimated days remaining: 4

4/24/2026

6-24”-123’ 7” dry SS

CZM-R

Rental CZM 125 (rig 8)

Billy

Jose G

Manns Project Steel Dragon Interior ($3,085.56)

26/1603

15060 Blue Mound Rd. Fort Wort

20-30”-300’

8-36”-120’

8-42”-120’

Contract price: $27,770 Dry

Price per hole: $771.39

Days on site: 2

Estimated days remaining: 17

4/24/2026

4-36”-68’ 7” dry SS

DF1

Robert

Kevin

BAR Lake Palestine LP1 Package 2 ($1,481.24)

26/0250

4362 CR 309. Frankston

40-30”-1570’

32-36”-1472’

100-30”-1000’ BOLLARDS

Contract price: $254,774.00 FULLY CASED TURNKEY

Price per hole: $1,481.24 INCLUDING BOLLARDS

Days on site: 12

Estimated days remaining: 28

4/24/2026

1-36”-79’ 0” with 55’ casing

Sany Mandarin

Jose A

Juan V

Miguel A

Alfonso

Ronnie

Josue

Griezman

Carmelo

Hector M

United Forming DBU Carter School of Business ($2,360.00)

26/2800

3000 Mountain Creek Pkwy. Dallas

53-24”-2080’

37-30”-1679’

37-36”-2062’

4-42”-264’

Contract price: $77,290.00

Price per hole: $590.00

Days on site: 17

Estimated days remaining: 23

4/24/2026

4-24”-110’ 4” dry SS

Sany Pikachu

Jonathan

Jose Z

Howard

Al Kline Cedar Hill COD ($11,135.00)

26/0051

2927 Emerald Sound Dr. Cedar Hill

200-12”-3000’

Price per hole: $85.00

Days on site: 2

Estimated days remaining: 0

4/24/2026

131-12”-1818’ 4” dry SS

Batman

Dash

Pete

Gerardo

Gustavo

Jose Inez

Wilbert

Omar

Toni

Eduardo